PUBLIC PROCUREMENT REFORMS: ISSUES AND CHALLENGES: THE CASE OF UGANDA

A.	BACKGROUND TO THE REFORMS

Effective public procurement systems are systems that are defined as offering a high level of transparency, accountability and value for money in the application of a procurement budget. They are critical to poverty reduction and AID effectiveness. Hence, all parties in the development process must have a vested interest in promoting this critical pillar of good governance: and to do so, in the context of an open macro economic framework that promotes open competition, the free functioning of markets and the allocation of resources based on comparative advantages.

The reforms in Uganda, commenced in 1997, as a process and a key milestone, or the first key event was the National Public Procurement Forum held at the behest of the Ministry of Finance, Planning and Economic Development (MOFPED) in Entebbe. The co-chairmen of the Forum were the Heads of the Central Tender Board (CTB) and the Government Central Purchasing Corporation (GCPC) and representatives of ministries, parastatals and district tender boards participated. No industry representatives or the private sector were involved.

UNCTAD/WTO International Trade Centre (ITC) backstopped the Entebbe Workshop with technical advise and financial assistance from the Swiss Government. The World Bank was also in attendance at the Forum, where it indicated its intention to conduct a Country Procurement Assessment Review (CPAR) in 1998.

There were two sources of pressure on the Government to review the performance of the public procurement system and to generate a restructuring plan. One was the realisation by the Government itself, that the old system could not deal satisfactorily with the emerging demands on the system in terms of transaction numbers, expanding value of procurement budgets, scale and technical complexity of procurement activities. These demands were being made against a backdrop of a lack of bureaucratic accountability and transparency and the absence of a culture of value for money procurement. Against this weak background, donors began to exert pressure on the Government to put in place the appropriate remedies.

In response, the Government created in May 1998 a twelve-man Task Force on Public Procurement Reforms comprising the private sector represented by Procurement and Logistics Management Association (PALMA) and the donor community by the World Bank and headed by Mr. Kalanguka-Kayondho. The Task Force was given comprehensive Terms of Reference and was meant to report to the Ministry of Finance, Planning and Economic Development within six months i.e., February 1999. in a nutshell, the Terms of Reference required the Task Force to:

- take into account the Entebbe Forum findings on the constrains in the existing system and what changes may be needed to rectify these;

- bring into consideration international best practices in formulating a reform programme to be implemented by the Government;

- pay attention to the findings of the CPAR and take these into consideration in the programme design; and

- submit to the Government a comprehensive procurement policy reform plan for approval and implementation.

The Task Force submitted its Report to the Government in March 1999, which identified widespread corruption and malpractice in the procurement system.

##### B.	FINDINGS OF THE TASKFORCE

In particular, the Task Force found that:

Trade Practices. Private sector participation in public procurement, particularly goods and services, is very minimal.  Local traders, suppliers, consultants, contractors, architects and engineers have not built enough capacity to participate in tenders advertised internationally and locally particularly when the values are large.  Local suppliers and contractors often do not have the capacity to raise credit, bid bonds and securities from local banks and insurance companies, in part due to the high rates of interest charged.

Suppliers who would like to participate in public procurement find the procurement procedures irrational and cumbersome. They are sometimes excluded when the procurement is too big and they are apprehensive of unfamiliar procedures. They are not well informed of how the procurement process functions, which renders the process open to abuse.  The private sector does not believe the public procurement process can move without a “push”. The private sector, however, would embrace clear, easy-to-follow guidelines if this minimises costs and facilitates business.

There are indications that over and under-invoicing in imports and local procurement are common practices.  This is attributed to mainly inside dealings.  However, long time lags and delays on the part of government to pay suppliers are some of the causes for over-invoicing.  Under invoicing is due to uncertainties relating to a supplier’s chances of winning a tender bid.

There is evidence of malpractice that affects public sector procurement; e.g. vehicle repair documents are often not used. Sometimes invoices, receipts and other documents are faked.  In other instances of government procurement, documents are “chased” by suppliers pushing them through the process in person.  The assumption is that “chasing” will not be successful without bribes, commonly known as the “kitu kidogo” or “speed money”.

Financial Framework: Most banks in the country have international connections.  They are able to issue letters of credit, bid bonds and other guarantees for compliance with tenders. The credit worthiness of the banks is guaranteed in that the Bank of Uganda supervises and ensures that only credit worthy and professionally managed banks are licensed to operate in the country. High interest rates (e.g. 18% – 25%) appear to be a hindrance for national suppliers to access credit. Similarly, some national bidders find the 10% requirement for bid bond too high, and they end up not participating in tenders advertised locally.

The Institutional Framework: The Central Tender Board (CTB) was the main overseer of the public procurement process in Uganda. The CTB derived its authority from the Tender Board Regulations of 1977 established under the Public Finance Act. Cap. 149. The Central Tender Board was established to regulate and control:

- The purchase or sale of government stores and equipment; and

- The award of government contracts for goods` services or works.

It approved purchases submitted to it by procuring entities. Such procurements were for goods, works and services above the threshold of Shillings 1 million for goods and Shillings 2 million for works and services.

The Government Central Purchasing Corporation (GCPC) was set up by Statute No. 3 of 1990.  The objectives of the GCPC were to procure government goods and services at the fairest prices, to ensure government gets value for money and to carry out the procurement functions expeditiously.  It acquired goods, supplied them to government departments and advised government on procurement policy and practices.

The Swiss Procurement Company (SWIPCO), a private contractor, performed the following functions under Contract with the Ministry of Finance:

- Advised the CTB to ensure that the professional capacity of the Board is strengthened and extended;

- Assisted procuring entities in preparing tender documents, performing evaluations, drafting contracts and supervising contract performance; and

- Provided training on procurement to staff at different levels of government.

Local governments – the district administration also engaged in public procurement through the District Tender Boards.  The local governments Financial and Accounting Regulations 1998, which derived from the Local Government Act 1997, regulated these.  Goods and services in districts are procured through these Tender Boards.

The Police Tender Board was created by The Police Statute No. 3 of 1994 for procuring goods works and services for the police force.  Procurements conducted through the Police Tender Board did not have to go through the Central Tender Board.

The Military Tender Board was created by the NRA Statute No. 3 of 1992 to cover supplies for the Army.  Procurements conducted through the Military Tender Board did not have to go through the Central Tender Board.

Weaknesses: Despite its implicit strengths, the old system also had a number of weaknesses.

- The Central Tender Board, which oversaw the procurement process in the country, had a set of disparate, (in the sense that the District Governments were not covered) and outdated procurement regulations and procedures.

- The responsibility for procurement was inconsistent among various procuring entities within the system.

- The government system operated through cash budgets that, because of a lack of coherent management attention to problems caused by this in the procurement area, made it an unreliable business partner.  These problems were compounded by impoverished management practices in the procurement sub-system both at the central and district administrations.

- Bureaucratic delays and lack of institutional co-ordination characterised the current procurement system in the country.

- Malpractice and unethical conduct also saddled the system.  There was a high incidence of vested interests, interference and insider dealings.  There were occasional cases of retroactive approvals of contract awards.

- Procurement knowledge and expertise at policy and operational levels were inadequate.  This implies that the personnel involved were severely handicapped concerning the requisite procurement skills.  Analysis had also revealed that apart from World Bank documents, the procurement system in the country lacked standard documents for use in specific contract situations.

- The lack of focus in the existing regulations and guidelines were giving rise to decisions, which were devoid of objectivity, accountability and transparency and resulted in a high incidence of corruption and high expenditure.

## C.		OBSERVATIONS ON NEEDS

- The Task Force found the following needs:

- A comprehensive legal framework and a coherent set of regulation/guidelines - these regulations/guidelines should focus on the entire supply-chain management process.

- Effective monitoring and auditing to ensure compliance with regulations/guidelines and performance.

- This calls for establishment of a management organisation to manage a restructured procurement system.

- Standard terms and contracts.

- Tenders should be open and advertised.

- Well co-ordinated procedures to make the system more transparent and streamlined.

- Sanctions to enforce professionalism and to punish offenders causing losses.

- Procurement expertise in each procuring entity.

- A deliberate effort is needed to develop capacity through organised staff training.

The Task Force proposed as follows:

## D.	TASK FORCE SUMMARY OF REORGANISATION NEEDED

- The proposed organisation review of the public procurement system should be harmonised with the on-going restructuring exercise in the civil service especially as it affected the Central Tender Board.

- The Task Force proposed that a National Procurement Policy Unit (NPPU) be established and that the CTB be restructured to perform all the functions of the NPPU set forth below.  The restructured CTB would also take over the advisory function of GCPC after its privatisation.  The tender awarding functions hitherto undertaken by CTB should be taken over by the new Ministry Contracts Committees.  Thus the restructured CTB would be a policy body with specific functions of monitoring, the public procurement system through other entities.

- The establishment of a restructured CTB as the NPPU would be effected through regulations under the Public Finance Act.

- NPPU would thus take the budgetary allocations for the restructured CTB.

- It was proposed that the restructured body should have the following features:-

- It should be free of political interference.

- The relationship between this body and other procurement entities should be clear.

- The body should also provide for the use on a value-added basis of third party agencies (internal or external to the Government) to offer expert advice to all entities.

- The NPPU would be an autonomous unit deriving funding from both the consolidated fund and through levies and service charges.

- The proposed body would have an organisation structure that reflects the new functions and status.

- The proposed body would also have a Consultative Committee composed of major stakeholders in the private and public sectors to advise the Director, NPPU on matters concerning the overall functioning of the public procurement system.  The Committee would  be composed of no more than 12 members from various disciplines and oriented towards the procurement profession.

- The membership of contracts committees to be created should consist of civil servants principally drawn from within the Ministry or procuring entity.

- Contracts committees are preferred to Tender Boards because in addition to Tender Board work, they will monitor progress of contracts approved.

Sustained management advice and assistance to support budgetary considerations in the area of expenditures for public procurement must be provided.  This was to be best provided through a central procurement management and policy office, the National Procurement Policy Unit. The NPPU was to be located within the Ministry of Finance. The head of the unit was to be graded at a level (e.g. Director level), which would ensure that NPPU could meet its responsibilities to Ministries and other procuring entities. The responsibilities for the NPPU included:

## E.	ROLE OF THE NATIONAL PROCUREMENT POLICY UNIT (NPPU)

Develop Procurement Policies:  This function included the issuance of:

- Policies at the macro level covering matters like participation in international trading agreements, use of international technical standards, preference for domestic industries and the application of environmental purchasing.

- Policies covering professional practice including contracting procedures, measurement of performance by the procuring entities, measurement of suppliers performance, supplier qualification procedures and supplier relationships.

- Develop Procurement Regulations and Procedures: This function included:

- The development, maintenance and updating of procurement law, regulations and procedures;

- The dissemination of legal and regulatory updates and amendments;

- The development of training materials on the requirements of the Law, Regulations and Procedures;

- Compliance with procurement law, regulations and procedures

- Developing and maintaining standard tender documents and standard conditions of contract;

- Providing help and advice to the contracting entities; and

- Establishing financial thresholds as required by law or regulation.

- Promote Professional Practice: There was a need for a co-ordinated approach to procurement if the government was to achieve best value in its use of public funds.  This co-ordination could be provided within a central policy unit, which, while recognising individual authority in the procuring entities, worked with these entities to:

- Develop and disseminate recommended procurement policies;

- Set professional standards;

- Develop a “code of business ethics";

- Provide professional advice and support to the individual procuring entities;

- Issue “good practice guides” in relation to procurement;

- Undertake research into the needs of procuring entities;

- Undertake research into domestic and international sources of supply;

- Develop a data base of information on which to base procurement decisions;

- Operate a professional development scheme for staff with purchasing and contracting responsibilities, including adherence to proper ethical standards;

- Promote economy by facilitating rationalisation of demand and intra-government contracting by means of “call off” and “running/ framework” contracts; and

- Rationalise standards for the procurement of information systems and equipment.

- Obtain Economic Benefits of Scale: Within the public sector, many individual procuring entities purchased similar goods and services. With few exceptions, those were being purchased independently with contract notices appearing in the national press on the same day for the same items from different procuring entities. If these purchases could be aggregated, it would result in prices that are more competitive, lower operating and maintenance costs and improved service for the procuring entities. It would also encourage domestic manufacturers to invest in plant and equipment.

Procurement responsibilities should remain within the procuring entities but joint contracting should take place where appropriate and beneficial to the parties involved.  Experience in other countries has shown that for joint contracting to be successful, procuring entities must work together to rationalise requirements, agree on contract specifications and determine who will be responsible for the contracting process.

The NPPU would help meet these challenges through a facilitating role to:

- Identify through its research function products or services purchased by more than one procuring entity that would benefit from joint contracting;

- Set up contracting working parties and invite members from the participating procuring entities;

- Act as secretariat to the working parties; and

- Report on results including savings achieved.

Joint contracts may be in the form of:

Call Off Contracts:  These are contracts under which a defined quantity of goods would be produced by the supplier and held in stock for ordering as and when required by individual purchasers, usually within a defined period

Framework Arrangements: These are arrangements covering a given period during which a supplier will provide goods, services or works to an agreed specification at an agreed price with agreed service levels. Contracts are formed when individual orders are placed against the arrangement

For these contract arrangements to operate successfully, the participating procuring entities must have ownership and commitment to the process. This can best be achieved by their involvement in all contracting activities: from production of specifications through to contract award and performance monitoring. In practice for each contract, only one entity will be responsible for letting the contract. This will usually but not necessarily be the largest purchaser. Whoever undertakes the process must agree on the contracting decisions with the other participants. For the framework arrangements an estimated quantity of requirements to be purchased during the contract period must be made known to the tenderers.  Also, there should be a facility for the contract/arrangement to provide choice of product or service if this is required by individual procuring entities. The process will not work well if standards are dictated to individual purchasers.  Variable prices for different purchase quantities, different geographical locations and different service levels may be established. However, for this arrangement to work, there must be a clear commitment to use the contracts by the participating entities.

Ensure Professional Input Into The Contracting Process: Procuring entities should train and develop professionally qualified staff for public sector procurement. To do this, it will be necessary to:

- Maximise the use of existing resources, possibly by developing a specialised multi-disciplinary contracting team that could provide professional advice and assistance to individual purchasing entities for major contracts. The responsibility for the contracting process, the contract award and the contract performance would remain with the procuring entity.  It would be a central function to co-ordinate this process.

- Employ external consultants to advise and assist with the contracting process. The selection of consultants for this work would be undertaken by means of competitive tenders in accordance with the procurement legislation.  Help in this process would be available from the central advisory function.  Help individual procuring entities undertake this process, it is recommended that the central policy unit issue guidance on best practice in “contracting for consultants”.

- Promote Effective Domestic And International Competition By Qualified Suppliers: To obtain best value, quality and service it is good procurement policy to encourage the most competitive and able suppliers to tender for your contracts. To achieve this objective, the NPPU and procuring entities must emphasise:

- Procedures which are fair, non discriminatory and transparent;

- Compliance by the purchaser with their obligations under the contract including the “terms of payment”;

- Standard conditions of contract;

- Requirements which are clear-- using performance and international specifications where possible;

- Rationalisation of needs and aggregation of demand to facilitate economic manufacture;

- Use of framework and call off contracts;

- Use of long term contracts “two or three years” to encourage investment;

- Good working relationships and trust between purchasers and suppliers. Model guidelines for developing good relationships.

Develop Management Information: A constituent part of any function must be the collection and management of information.  Among the data that procuring entities should provide routinely are:

- the number and monetary value of contracts awarded during the year (or for a shorter period of time);

- the extent of competition; and

- the types of articles purchased.

- Establish a Disqualified Suppliers Database: There is a need to maintain a database of suppliers who have been disqualified by procuring entities so that all procuring entities have access to this information as part of their supplier assessment procedures.

F.	PROGRESS TO DATE

The question is what has happened since these recommendations were made in February 1999?

First, the Government accepted the findings of the Task Force and concurred with all its recommendations in June 1999.

Second, the Ministry, based on the Task Force recommendations, submitted in November 1999 a Cabinet Document seeking the approval of the Cabinet Minister to proceed with the creation of a Procurement Reform Implementation Unit (PRIU) in the Ministry and to task it with their Implementation of the Task Force recommendations. This was approved in January 2000.

Third, key activities on the reform agenda of the PRIU have found reflection in the Poverty Reduction Support Credit (activities and outputs) Matrix, thereby committing the Government to execute the reform activities within a given time table acceptable to all stakeholders, inclusive of the donors.

Since the approval of the Cabinet Memorandum on the Procurement Reforms, the Government has proceeded with the timely implementation of the key reform activities. These are evident from the:

- promulgation of the Public Finance (Procurement) Regulations (Statutory Instrument) in March 200 which came into effect in May 2001, ad a transitional step to an Act;

- appointment of senior Management personnel to the PRIU to prepare for the transition from a Central Tender Board structure to an autonomous authority;

- enactment of a law to replace the Statutory Instrument in 2002;

- issuance of Regulations, Reporting Forms and Guidelines attendant on the Act in 2003 in order to operationalise the system;

- preparation and release of standardised bid documentation for works, services and supplies in three variants each for complex, medium and simple procurement activities, respectively.

This is where we are in terms of the Reform Agenda at this point. Other key items remain to be implemented. Sufficient to mention four critical ones. These are:

- Harmonization: The harmonization of procurement policies and practices between the Central and the Local Government systems is a key activity. Two prior conditions have to be satisfied before harmonization can take place.

- The first is the passing of the Procurement Bill by Parliament and the promulgation of the attendant Regulations to the Bill. While the Bill seeks to provide the legal basis for the harmonization (inclusive of regulatory oversight by the PRIU for systemic performance of the Local Government Procuring Entities), the real burden of harmonization will fall on the attendant Regulations to the Bill. I am happy to inform the Review that the PRIU has already prepared the draft Regulations to the Bill. Also, we have had fruitful discussions with the Ministry of Local Government – which is in possession of copy of the draft Regulations.

- The second relates to the capacities of the Local Government system to operate under the draft Regulations in question under the harmonized system. What are the precise institutional and manpower arrangements and practices in place?  Are these adequate, and if not, what corrective measures are required? Should we wait until harmonization becomes imminent before we begin to look into the problems, if any? To await the passing of the Bill could seriously impair the Government’s quest to subject public procurement at all levels of Government to standardized best practices at the earliest possible opportunity. Hence, the PRIU is proposing co-jointly with the Ministry of Public Service and the Ministry of Local Government to conduct a rapid result survey to assess the realities on the ground in the local government procurement system as an integral part of its current Work Plan.  This will enable the PRIU to establish what types of support may be required to ensure compliance on the part of the Local Government system with the new dispensation, once it comes into place.

- Benchmarking: The issue of benchmarking performance is another plank in the Work Plan of the PRIU. The key justification for all reforms is that the proposed changes will generate a stream of net benefits, however defined, to the public (in excess of what the old system did). Otherwise there is no need for innovation and change. How are these benefits to be specified in terms of quantifiable outputs and or qualitative improvements and how is progress in achieving them, or otherwise, to be objectively measured and verified from one point to another? And how do we determine the final time horizon for the full delivery of outputs and the intervals for measurements of progress? This is not a simple exercise, even though it will have to be kept as simple as possible, and it will have to be focused on the performance of the Procuring Entities, the PRIU and the contractors. It is an exercise that will require the inputs of many stakeholders groups, not least the oversight agencies, and it is one that will preoccupy the PRIU in the current Financial Year.

- Private Sector: In the design of the reforms, the focus has understandably been, solely on the public entities of Government, based apparently on two assumptions:

(a) 	public officials, are deviant in respect of procurement;

(b) 	efficiencies in procurement can only be achieved by improved public performance.

Both of these may be true to some extent. But we must not lose sight of the old adage that, “It takes two to tango”. Somehow, in the deliberations on the reforms, we have not taken fully into account the private sector, particularly the associations of the contracting community and the fact that they are the other critical party to all procurement activities. Hence, the extent to which the reforms will succeed in producing Value-For-Money and the benefit of efficiencies and effectiveness, depends invariably on their cooperation in changing the ways in which they do business and by having them adopt higher standards in contracting with the Procuring Entities.

The issue here is ‘Where do we start?’ In the public domain, information on the market place is limited. We have no database on procurement input prices, be they for works, services or supplies.  Moreover, there is very limited information available on the sizes, core competences and performance record of providers.  Nor do we have any idea as to which associations represent which contracting group and how many contractors belong to which associations. The void in market information is a serious handicap in terms of the PRIU developing a constructive dialogue with the private sector in order to come up with an operational plan to improve market information and private sector participation public procurement and in promoting best practices. The development of such a scheme is an important strand of the current PRIU Work Plan. It is envisaged that the focus of the scheme will be on:

  - developing a Contractors’ Register based on proven capacities, recognized, core competences (disciplines) and objective performance record;

  - preparing a database on providers’ prices;

  - working with the Associations of Contractors to develop a code of conduct, have their members adhere to it, and discipline errant contractors for non-compliance;

  - instituting mechanisms for the sharing of information on market conditions and procurement opportunities; and

  - networking institutions capable of providing sustainable training in procurement over the long-term.

- Stakeholders: An issue of much concern to the PRIU, and which constitutes another element of its Work Plan, is stakeholder connectivity. Procurement reform, as with all reforms in the governance sector, has many partners linked to the process, whether:

(a) 	directly;

(b)	indirectly;

(c) 	public interest bodies.

Each partner which has a specific role to play in the process. The direct partners are the Procuring Entities and the contractors. The indirect ones fall into three groups:

(a) 	the regulatory and oversight bodies, i.e., the IGG and Auditor General and the PRIU;

(b) 	subject entities, i.e. the Ministry of Public Service, the Ministry of Local Government and the PRIU;

(c) 	the donors and the Ministry/regulatory authority (PRIU), the Ministry of Public Service and the Ministry of Local Government.

Finally, there are the public interest groups, largely the Non-Governmental Organizations, which perform a dual role of remote monitoring of procurement performance by Procuring Entities and a direct advocacy role for the adoption of best practices in public procurement. An efficient and effective system must develop institutional inter-linkages between all interested parties and structured mechanisms for periodic exchange of information on different aspect of systemic performance in order to continuously infuse the system with best practices. The PRIU is working assiduously to put structures in place to take advantage of the synergies such cooperation will invariably offer.

Once the institutional and legal framework is completed, hopefully by the end of this calendar year (2003), the focus will then shift completely onto the operational dimensions of the Authority and the Procuring Entities in order to enable the reform system to deliver fully on its mandate.

This is not to say that the PRIU is not providing a stopgap operation. It is in order to prevent a regulatory vacuum from developing in the system. But it can be no substitute for the authority itself. More importantly, it recognises that two critical functions of the authority will be in order for the new system to function:

  - the building of capacity (institutional and human) in the procuring entities: which are nor completely responsible for the execution of their entire procurement budget – and has taken far reaching measures in this regards both in terms of modular (a) instructional training and (b) on-the-job transfer of skills; and

  - the exercise of its audit, inspection, investigation and review functions as a regulatory body. Here again, action has been taken to ensure that this capacity will be in place.

Where we may be behind is in the development of the allied and related capacities of the authority to be created in preparation for it to be fully operational once the new Act is brought into effect. Outstanding agenda items in this regard are the appointment of staff, the development of database, the introduction of a computerised WAN and LAN information dissemination and network systems to publicise procurement opportunities and award decisions, e.t.c.,

But no doubt significant progress has been made to date and to o small measure due to the combined assistance of the contracting community and donors. In the context of the latter, we have found the Procurement Technical Working Group, comprising of donors and Government, to have been a most useful consultative mechanism in assisting the PRIU to moving the reforms focus in respect of its activities and outputs schedule as we have found the PRSC Matrix.